## Sheet1
Payload Sub-Systems | Test/Analysis/Inspection/Demonstration/Traceability | Pass/Fail Criteria
ZES | Simulated connection with payload sub-systems using arduino to show data format, flow, an management for the ZES board. | Simulation connection with ardiuno and data frame generation needs to account for potential risks with corrupted frames.
Rila | Uses arduino to generate frames and is connected with ZES board. Additional corupted frames are added to simulation to act as demonstartion to how system reacts to corrupted data. (UART) | Simulation with ardiuno for data frame generation and deteriming risks remidis/protocals for corrupted frames.
Magnetometer | Similarly to Rila, uses ardiuno for simulation of data frames and corrupted data frames as means of testing, analysis, and demonstration. We also use APID structure to help format the data for the magnetometer (UART) | Simulation with ardiuno for data frame generation and deteriming risks remidis/protocals for corrupted frames.
ADXL-355 Accel. | Requires definition upon I2C connection with ZES. This shall be done using a cheaper model (LIS2DW12 accelerometer) to simulated data frames generation and I2C conenction. | Uses simulation with LIS2DW12 accelerometer to map out I2C connection with ZES and frame generation/data packet handaling.
MS1002 Accel. | Simlar to ADXL-355; will uses LIS2DW12 accelerometer as a substitue for simulation purposes while also further defining digital interface and ADC selection. | Fully define ADC selection and how that selection defines the digital interface/ data format of the accelerometer.
ICD Closure Status | Verification Plan
ICD-100 | Define volatge ranges and allowable tolerances, current draw by operational modes, fault response behavior and power-up sequencng (simulation).
ICD-101 | Requires integration of packet structure of all payload subsystems; not just modes A and B for ZES. Byte mapping and CRC implementation details are also needed, which can be compared with simulation.
ICD-102 | Requires command structure and mode switching definitions, as well as error handling and retry logic (uses simulated results/methods).
ICD-103 | Define housekeeping fields with sensor health reporting, status flags/fault indicators, and telemtry for voltages/currents/temeprature. (MS1002 and Magnetometer)
ICD-104 | Requires wiring schematics/maping.
ICD-105 | Completed using estamiations based on peak power consumptions. Furtehr verification can include thermal testing of each component runing at average and peak power over time.
ICD-106 | Define grounding scheme, noise susceptiblility, and cable shielding requirements for all payload subsystems (where necessary).